## Sheet1
Sprint Phase | Tasks | Details | Duration | Owner | Status
Planning | Requirements Gathering | Identify required microservices: Auth-Service, Customer-Service, Product-Service, Cart-Service, Order-Service. Define interactions between services via API Gateway. | 1 day | Team Lead | completed
Planning | Architecture Design | Design the microservices architecture. Set up the Eureka Server for Service Registry and Discovery. Set up the API Gateway for routing requests. | 1 day | Architect | completed
Development | Day 1 | Eureka Server & API Gateway Setup: Set up Eureka Server for service registration and discovery. Implement API Gateway to route requests to microservices. | 1 day | Developer | completed
Development | Day 2 | Customer-Service Development: Develop CRUD operations for customer profiles. Integrate with Auth-Service to handle customer data upon registration. | 1 day | Developer | completed
Development | Day 3 | Product-Service Development: Build functionalities for managing products, including categories and search. Implement APIs for product CRUD operations. | 1 day | Developer | completed
Development | Day 4-5 | Cart-Service Development: Develop features for managing the shopping cart, including adding, updating, and deleting items. Integrate with Product-Service to fetch product details. Implement the `item_entry` table to store individual cart items. | 2 days | Developer | completed
Development | Day 6 | Order-Service Development: Implement order processing functionalities, including placing orders and tracking status. Integrate with Cart-Service to process the cart items during order placement. | 1 day | Developer | completed
Development | Day 7-8 | Auth-Service Development: Create registration and login functionalities. Implement JWT token generation and validation for secure access. | 2 days | Developer | completed